## Sheet1
| 2025-02-02 | 2025-02-09 | 2025-02-16 | 2025-02-23 | 2025-03-02 | 2025-03-09 | 2025-03-16 | 2025-03-23 | 3/30/25 | 2025-04-06 | 2025-04-13 | 2025-04-20 | 2025-09-08 | 2025-09-22 | 2025-10-20 | 2025-11-10 | Date
Learn React Native Basics | [16 empty] | 2025-02-07
Design and Plan UI Layout | [16 empty] | 2025-02-10
Install dependencies for Flask (Python) | [9 empty] | Not started | [6 empty] | 2025-02-10
Plan Database Structure in Firebase | [9 empty] | In Progress | [6 empty] | 2025-02-21
Set Up Flask Structure and Environment | [9 empty] | Completed | [6 empty] | 2025-02-24
Set Up Firestore Database | [9 empty] | Behind Schedule | [6 empty] | 2025-02-25
Design Logic for Backend Info Storing | [16 empty] | 2025-03-14
Code general application outline | [16 empty] | 2025-03-14
Integrate Service for Feedback | [16 empty] | 2025-03-14
Set up authentication through Firebase | [16 empty] | 2025-03-19
Set up data sending/fetching to Firestore | [16 empty] | 2025-03-27
Integrate Plaid API for Bank Data | [16 empty] | 2025-03-26
Establish live graph and chart functions | [16 empty] | 2025-04-02
Handle Sign in/Sign up | [16 empty] | 2025-04-05
Integrate Data Management Systems | [16 empty] | 2025-04-03
Implement graph and design home page | [16 empty] | 2025-04-17
Design analysis page | [16 empty] | 2025-04-12
Develop Backend APIs for Records | [16 empty] | 2025-04-09
Finalize Database and Backend Structures | [16 empty] | 2025-04-18
Design education page | [16 empty] | 2025-04-23
Integrate Alerts/Sounds | [16 empty] | 2025-04-23
Join Firestore Database | [16 empty] | 2025-09-20
Modify UI to Include Relaxing Features | [16 empty] | 2025-10-18
Plaid API Integration | [16 empty] | 2025-10-20
Fully integrate Front-end and Back-end Operations | [16 empty] | 2025-11-10