## Sheet1
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
2.2.1.1 | API Response Time Test | API response time should be ≤ 500ms under normal load. | Use Postman or to send multiple requests to Flask endpoints. Identify bottlenecks using Flask debugging and profiling tools. | DONE 4/24/24 | Hoang-Nghi Nguyen
2.2.1.2 | Bank Transaction Fetching | The system successfully fetches and updates bank transactions for sandbox simulation tests. | Simulate API calls to Plaid with valid and invalid credentials. Monitor response times and error handling when Plaid's service is down. | DONE 4/24/25 | Hoang-Nghi Nguyen
2.2.1.3 | ML Model Accuracy | The ML model provides at least 85% accuracy in classifying transactions | Feed test datasets with labeled transactions and compare output classifications. | DONE 4/14/25 | Hoang-Nghi Nguyen
2.2.1.4 | Database Read/Write Performance | Read/write operations complete in ≤ 200ms for 90% of requests. | Simulate concurrent database queries (fetch transactions, store new data). | DONE 3/3/25 | Hoang-Nghi Nguyen
2.2.1.5 | End-to-End Module Functionality | Each core app function works correctly, including authentication, data fetching, ML analysis, and storage. | Test individual modules in isolation (e.g., authentication, API calls, ML predictions). | DONE 4/14/25 | Hoang-Nghi Nguyen
2.2.1.6 | Transaction Categorization & Display | Transactions retrieved from Plaid are correctly categorized, stored, and displayed in the app. | Fetch sample transactions and check if categories (e.g., "Food", "Rent") match expected results. Validate ML model outputs for accuracy and consistency. Check if categorized data is stored properly in Firebase Firestore. | DONE 4/14/25 | Hoang-Nghi Nguyen
2.2.1.7 | Expense Tracking & Budgeting | The app correctly tracks user expenses and provides budgeting insights without errors. | Input various expense types and verify that total spending updates correctly. Compare budget warnings/recommendations with expected calculations. Simulate multiple expense entries over time to ensure long-term tracking consistency. | DONE 4/14/25 | Hoang-Nghi Nguyen
2.2.2.1 | Home Tab | The home page of our app will provide helpful and comprehensive material on current budget status and take no more than 4 minutes to learn how to navigate. | Groups of five students will tasked to engage with the home page and understanding will be assessed and polled. | DONE | Camille Embree
2.2.2.2 | Tracking/Analysis Tab | This tab will provide accurate and legible charts and graphs regarding the users recent spending. | Sets of test data will be written into the application and user tests will be conducted with five students to determine comprehensiveness. | DONE | Camille Embree
2.2.2.3 | Financial Literacy Tab | Relevant and helpful information such as financial articles, scholarship opportunities, and investment recommendations will be displayed in an engaging and user friendly manner. | Five students will be asked to view three sets of example financial literacy tabs and determine how accessible and visually engaging they are. | DONE | Camille Embree
2.2.2.4 | Account Page | The account page will accept only valid user information and store the data securely. | Run a method to pull sets of valid and invalid inputs out of a test database and ensure that each value successfully returns true or false. | DONE | Camille Embree
2.2.2.5 | Sounds | The application will produce sounds to indicate certain buttons/options being selected. | A sandbox environment will be utilized to ensure that the correct sound goes off 95% of the time each vocal button is pressed. | DONE | Camille Embree
2.2.2.6 | Alerts | Push notifications will be sent to users who so choose, reminding them of budgetary status or lower-priced options. | Send and track a minimum of ten push notifications to mobile device using the Delivery Log within the Apple Push Notification Console. | DONE | Camille Embree